## Sheet1
Service | service owner - to be kept informed with any migration plans | Current server | [8 empty] | Predicted Storage Needs for application/user data |  |  |  | immediate action needed to keep service running (before server virtualisation) | Proposal for new virtual server | [16 empty] | Resilience |  | Migration Plan/ Testing needed | Additional Notes
|  | server name | physical/ virtual | age of server (date it arrived at UCL) | CPU | Memory | local storage currently available (GB) | OS | Application Middleware | Application | Now (Jan/Feb 2011) | By Summer 2011 | By Summer 2012 | By Summer 2013 |  | Service | server name | Which Stack? (High Availability/ Business Hours/ Development) | size of new VM (small/ medium/ large) | CPU | RAM (Gb) | standard local server storage requirements (Gb) | additional local server storage requirements (Gb) - T1 | additional local server storage requirements (Gb) - T2 | storage on an NFS mount needed - T1 | storage on an NFS mount needed - T2 | COST | OS | Application Middleware | Application | Ease of Migration | Priority for migration to VM stack (urgent/high/ medium/low) | Current method | Proposed method
WEB APPS SERVERS (WIKI, OPINIO, MYPORTFOLIO) | [15 empty] | WEB APPS SERVERS (WIKI, OPINIO, MYPORTFOLIO)
production Wiki | ltss-team@ucl.ac.uk isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk | webapps-a | physical (Wolfson House) | 2008-01-25 | 2 x quad core Xeons | 8GB | 40 Gb Free (557 Gb Total) | Ubuntu 6.06 | Apache Tomcat | Atlassian Confluence 3.4.5 | ~2.5 Gb attachments stored at present locally on this phyical server that would need to be migrated | 4 Gb | 7 Gb | 10 Gb | - | Production Wiki and Production Opinio | vmwebapps-a |  | small | 2 | 4 Gb | 40 | 0 | 0 | 0 | 0 | 2702 | RHEL6 | latest version of apache, tomcat (standard ISD build with using standard RPMs) | latest version of Atlassian Confluence and ObjectPlanet Opinio |  |  | none, single application server, no failover (although uses central mysql-server which has master/slave resilience) | VMware resilience
production Opinio | ltss-team@ucl.ac.uk isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk | webapps-c | physical (Wolfson House) | 2008-08-07 | 2 x quad core Xeons | 8GB | 7 Gb Free (278 Gb Total) | Ubuntu 6.06 | Apache Tomcat | ObjectPlanet Opinio 6.3 | 40Mb of user uploaded files for Opinio (CSS for small logos they may add to their surveys, likely to stay small) | 100 Mb | 300 Mb | 500 Mb | -
production Myportfolio | ltss-team@ucl.ac.uk isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk | [7 empty] | Apache PHP | (open source) Mahara 1.3.3 | 1.2 Gb local data (users upload documents, images, pdfs, etc as part of their portfolio - potential to get very big as the service becomes more popular) | 90 Gb | 110 Gb | 130 Gb | - | Production Myportfolio | vmwebapps-b |  | small | 2 | 4 Gb | 40 | 130 | 0 | 0 | 0 | 3638 | RHEL6 | latest version of apache, php (standard ISD build with using standard RPMs) | latest version of open source Mahara |  |  | none, single application server, no failover (although uses moodledb mysql which has master/slave resilience) | VMware resilience
MOODLE SERVERS | [15 empty] | MOODLE SERVERS
Production Moodle | ltss-team@ucl.ac.uk isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk | moodle-a | physical (Wolfson House) | 2008-01-25 | 2 x quad core Xeons | 8GB | 500 Gb Free (1,117 Gb Total) | Ubuntu 6.06 | Apache v... PHP 5.2.5 | (open source) Moodle 1.9.9 + (application code and copy of user data) | user data 520 GB (synced hourly between the 3 moodle-a, -b and -c application servers) and we expect this to grow … It seems to be going up at around ~20Gb a month | 640 Gb | 880 Gb | 1,120 Gb | - | Production Moodle | vmmoodle-nfs |  | small | 2 | 4 Gb | 40 | 1120 | 0 | 0 | 0 | 10766 | RHEL6 |  |  |  | high importance | having 3 application servers under server load balancing (SLB), if one fails it drops out of the farm and the users are automatically redirected. Moodle-a is the 'master' server, running the cron job and holding the most up to date copy of the 'moodledata' user data, this data is rsync'd to the other 2 servers each houtr. If moodle-a failed manual intevention would be needed to switch (the NFS?) to one of the other servers | would we need multiple application servers? Perhaps for capacity but not for resilience as that would be taken care of by the VM software. The 'moodledata' would be on the new vmmoodle-nfs so the rsync method would no longer be needed, the vmmoodle-nfs server would need to be extra resilient as without if the moodle service would become unavailable | Migration plan: move moodledata to new vmmoodle-nfs server. Then add in new vmmoodle-a application server to the farm and test I/O with additional VM in SLB farm. | we wouldn't want to virtualise Moodle until we were sure of the process, eg that wiki, opinio, myportfolio and moodle pre-production had moved across smoothly, also Moodle needs a large amount of storage space.
[17 empty] | vmmoodle-a | HA | medium | 4 | 8 Gb | 60 | 0 | 0 | 0 | 0 | 5115 | RHEL6 | latest version of apache, php (standard ISD build with using standard RPMs) | latest version of Moodle |  | high importance
[17 empty] | vmmoodle-b | HA | medium | 4 | 8 Gb | 60 | 0 | 0 | 0 | 0 | 5115 | RHEL6 | latest version of apache, php (standard ISD build with using standard RPMs) | latest version of Moodle |  | high importance
|  | moodle-b | physical (Torrington Place) | 2008-01-25 | 2 x quad core Xeons | 8GB | 500 Gb Free (1,117 Gb Total) | Ubuntu 6.06 | Apache v... PHP 5.2.5 | [7 empty] | vmmoodle-c | HA | medium | 4 | 8 Gb | 60 | 0 | 0 | 0 | 0 | 5115 | RHEL6 | latest version of apache, php (standard ISD build with using standard RPMs) | latest version of Moodle |  | high importance
|  | moodle-c | physical (Wolfson House) | 2008-01-25 | 2 x quad core Xeons | 8GB | 500 Gb Free (1,117 Gb Total) | Ubuntu 6.06 | Apache v... PHP 5.2.5
pre-production moodle |  | moodle-pp | physical (Torrington Place) | 2006-01-17 | 2 x quad core Xeons | 4GB | 11 Gb Free (136 Gb Total) | Ubuntu 6.06 | Apache v... PHP 5.2.9 | at least 2 copies of Moodle: current live and next version for testing Moodle functionality prior to roll out (application code and subset of user data stored locally on the server). | 1 copy of a subset of the 'moodledata' (user data) per Moodle instance stored locally on the server. | 50 Gb | 70 Gb | 100 Gb | - | Pre-production (UAT) moodle moodle-test (mainly by ISD Training and Knowledge team for testing Moodle user content) Pre-production (UAT) myportfolio | vmmoodle-uat |  | small | 2 | 4 Gb | 40 | 100 | 0 | 0 | 0 | 3422 | RHEL6 | latest version of apache, php (standard ISD build with using standard RPMs) | latest version of Moodle application code, moodledata should be on SAN and db should be on (new) mysql-pp server so that pp environment replicates production environment as closely as possible in order to make our testing as useful as possible |  |  | none | VMware resilience
moodle-test | [9 empty] | copy of current production Moodle, used (mainly by ISD Training and Knowledge team) for testing Moodle user content | 1 copy of a subset of 'moodledata' (user data) per Moodle instance stored locally on the server. |  |  |  | - | [14 empty] | copy of current production Moodle, used (mainly by ISD Training and Knowledge team) for testing Moodle user content
Pre-production myportfolio | [9 empty] | at least 2 copies of myportfolio: current live and next version for testing prior to roll out (application code and copy of user data stored locally on server). | 1 copy of a subset of the user data per myportfolio instance stored locally on the server. |  |  |  | - | [14 empty] | at least 2 copies of Mahara: current live and next version for testing prior to roll out (application code and copy of user data stored locally on server).
moodle-archive | [9 empty] | previous versions of Moodle, available to users in read only form (application code only, user data is currently stored on ifsp-unixfs5) | moodle-archive is for end users so will need the full moodledata. ~350 Gb user data is currently stored on ifsp-unixfs5. The plan is to build up a read only user archive copy of Moodle each year and keep up to the last 5-7 years live for users to access | 700Gb | 1,229 Gb | 2,560 Gb | user data is on borrowed/temporary space on ifsp-unixfs5 which is not guaranteed, by summer 2011 we will need an additional 640Gb to hold the 2010/11 archive (on top of the ~350Gb for the 2009/10 archive) | moodle-archive | vmmoodle-archive |  | small | 2 | 4 Gb | 40 | 0 | 2560 | 0 | 0 | 5774 | RHEL6 | latest version of apache, php (standard ISD build with using standard RPMs) | several instances of Moodle (one for each previous years up to 7 years) |  |  | none, and user data is on 'borrowed/temporary' space on ifsp-unixfs5 which is not guaranteed | VMware resilience
MYSQL SERVERS | [15 empty] | MYSQL SERVERS
Master MySQL server for Moodle, Myportfolio, Opinio | mysql-support@ucl.ac.uk isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk | moodledb-c | physical (Wolfson House) | 2009-08-07 | 2 x quad core Xeon X5570 | 24GB | 155 Gb available on /data, 3 Gb available on /tmp | Ubuntu 6.06 | Apache | MySQL 5.0.89 | ?? Gb in use on /data | 322 Gb on /data, 3 Gb on /tmp | 400 Gb on /data, 4 Gb on /tmp | 500 Gb on /data, 4 Gb on /tmp | - | MySQL Master/Slave for Production Moodle, Myportfolio and Opinio | vmmoodledb-a | HA | large | 8 | 16 Gb | 100 | 0 | 0 | 0 | 0 | 9947 | RHEL6 | MySQL |  |  | high importance | 2 way replication of database between master/slave. If master fails manual intervention needed to change DNS so applications point to other server | Initially use DNS manual failover, may investigate other options | migrate slave to vm, switch DNS, trial during advertised at risk period, switch back to physical server as master if problems, if no problems migrate other server to virtual | the moodle database can be a bit of a bottleneck on Moodle performance so we’d need to carefully plan the spec and migration of these servers… Migrate
Slave MySQL server for Moodle, Myportfolio, Opinio |  | moodledb-d | physical (KLB) | 2009-08-07 | 2 x quad core Xeon X5570 | 24GB | 156 Gb available on /data, 3 Gb available on /tmp | Ubuntu 6.06 | Apache | MySQL 5.0.89 | ?? Gb in use on /data | 322 Gb on /data, 3 Gb on /tmp | 400 Gb on /data, 4 Gb on /tmp | 500 Gb on /data, 4 Gb on /tmp | - |  | vmmoodledb-b | HA | large | 8 | 16 Gb | 100 | 0 | 0 | 0 | 0 | 9947 | RHEL6 | MySQL |  |  | high importance
Master MySQL server for general services including wiki, lecturecast |  | mysql-c | physical (Wolfson House) | 2007-07-14 | Dell Poweredge 2950, 4 x 300GB disk, ~830GB total space | 4GB | 311 Gb available on /data, 850 Mb available on /tmp | Ubuntu 6.06 | Apache | MySQL 5.0.89 | ?? Gb in use on /data | no additional requirements on /data, additional 1 Gb requirement on /tmp | no additional requirements on /data, additional 2 Gb requirement on /tmp | no additional requirements on /data, no additional requirements on /tmp | - | MySQL master/slave for general services including wiki, lecturecast | vmmysql-a | HA? | large | 8 | 16 Gb | 100 | 0 | 0 | 0 | 0 | 9947 | RHEL6 | MySQL |  |  |  | as above | as above | as above | Note from Vivek: Please note that my guesstimates on the /tmp is based on the assumption that no major data load requirements into MySQL will come through this period. Also I have not taken into consideration the increase in the memory requirement as this will be known only if there is a change in the data access pattern and/or data load pattern. I will nevertheless intimate atleast 6 months in advance if there is a memory requirement on any of the servers.
Slave MySQL server for general services including wiki, lecturecast |  | mysql-d | physical (Torrington Place) | 2007-02-09 | IBM x345, 4 x 72GB disks, ~200GB total space | 4GB | 26 Gb available on /data, 485 Mb available on /tmp | Ubuntu 6.06 | Apache | MySQL 5.0.89 | ?? Gb in use on /data | ideally 10 Gb additional on /data required, additional 3 Gb requirement on /tmp | additional 50 Gb additional on /data, additional 4 Gb requirement on /tmp | additional 50 Gb additional on /data, no additional requirements on /tmp | new internal hard disks need to be fitted in mysql-d, they are due to arrive at UCL the week of 14/02/2011 |  | vmmysql-b | HA? | large | 8 | 16 Gb | 100 | 0 | 0 | 0 | 0 | 9947 | RHEL6 | MySQL
[16 empty] | mysql development server | vmmysql-dev | dev stack | medium | 4 | 8 Gb | 60 | 0 | 0 | 0 | 0 | 5115 | RHEL6 | MySQL
[15 empty] | we have no UAT MySQL server for Moodle which prevents safe and thouorgh testing for services such as Moodle | MySQL UAT for UAT Moodle, Myportfolio and Opinio | vmmoodledb-uat | dev stack? | large | 8 | 16 Gb | 100 | 0 | 0 | 0 | 0 | 9947 | RHEL6 | MySQL
DEVELOPMENT SERVERS (FOR MOODLE, MYPORTFOLIO, WIKI, OPINIO, MYSQL) | [15 empty] | DEVELOPMENT SERVERS (FOR MOODLE, MYPORTFOLIO, WIKI, OPINIO)
wasdev-a moodle-dev, myportfolio-dev, nagios | ltss-team@ucl.ac.uk isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk mysql-support@ucl.ac.uk | wasdev-a.ucl-0 | physical | 2007-07-14 | 2 x 2GHz quad core | 4GB | 540 Gb Free (830 Gb Total) | Ubuntu | Apache, php, mysql | [8 empty] | dev stack | small | 2 | 4 Gb | 40 |  |  |  |  | 2702 | RHEL6
wasdev-b was subversion, now empty? |  | wasdev-b.ucl-0 | physical | 2007-07-14 | 2 x 2GHz quad core | 4GB | 200 Gb Free (830 Gb Total) | Ubuntu | Apache, php, mysql | [8 empty] | dev stack | small | 2 | 4 Gb | 40 |  |  |  |  | 2702 | RHEL6
wasdev-c moodle-dev server (also mysql-dev at the moment) |  | wasdev-c.ucl-0 | virtual, needs migrating to dev stack | virtual | virtual | 4GB | 40 Gb Free (110 Gb Total) | Ubuntu | Apache, php, mysql | [5 empty] | already virtual, could be moved to dev stack easily |  |  | dev stack | small | 2 | 4 Gb | 40 |  |  |  |  | 2702 | RHEL6
ats-a.ucl-0 wiki-dev |  | ats-a.ucl-0 | virtual, needs migrating to dev stack | virtual | ? | ? | ? | ? | ? | [5 empty] | already virtual, could be moved to dev stack easily |  |  | dev stack | small | 2 | 4 Gb | 40 |  |  |  |  | 2702 | RHEL6
CENTRAL SECURE WEB SERVERS | [15 empty] | CENTRAL SECURE WEB SERVERS
wwwa-a Production web Server | isd-ats@ucl.ac.uk is-webteam@ucl.ac.uk | wwwa-a | physical | 2004-06-24 | [11 empty] | - | - | - | - | - | - | - | - |  |  | - |  | - | - | - | - | - | - | - | - | -
wwwa-b failover/dev for wwwa-a |  | wwwa-b | physical | 2003-05-06 | [11 empty] | - | - | - | - | - | - | - | - |  |  | - |  | - | - | - | - | - | - | - | - | -
Production Web Server (wwwa-c) AWC Online Giving IRIS Experts iTunes HR STBS Slade Seascape project QUIRC |  | wwwa-c | physical | 2008-01-15 | 2 x quad core Xeons | 4GB |  | Ubuntu | [7 empty] | Production Web Server (with some of the following apps: AWC Online Giving IRIS Experts iTunes HR STBS Slade Seascape project QUIRC) | vmwwwa-? (for general purpose/departmetal apps?) | ? | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | RHEL6
wwwa-d failover/dev for wwwa-c |  | wwwa-d | physical | 2008-01-15 | 2 x quad core Xeons | 4GB |  | Ubuntu | [9 empty] | dev stack | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | RHEL6
Production Web Server (wwwa-e) Software Database blogs Subversion, Trac SPS (Student Psychological Services) Mediacast email Dropbox Comprep tools TARA STACK (Moodle maths tool) |  | wwwa-e | virtual (but not on central stack) | virtual | virtual | 4GB |  | RHEL5 |  |  | subversion needs local storage, does not work well if used via NFS software database download files (NFS mounted from ifsp-unixfs6) 202Gb | subversion needs local storage, does not work well if used via NFS software database download files: 300Gb | subversion needs local storage, does not work well if used via NFS software database download files: 350Gb | subversion needs local storage, does not work well if used via NFS software database download files: from ifsp-unixfs6) 400Gb | already virtual, could be moved to dev stack easily. This would let this server take advantage of VMware resilience | Production Web Server (with some of the following apps: Software Database blogs Subversion, Trac SPS (Student Psychological Services) Mediacast email Dropbox Comprep tools TARA STACK (Moodle maths tool)) | vmwwwa-? (for ISD/HR apps?) | ? | small | 2 | 4 Gb | 40 | subversion needs local storage, not NFS |  | swdb needs NFS mount |  | #VALUE! | RHEL6
wwwa-f failover/dev for wwwa-e |  | wwwa-f | virtual (but not on central stack) | virtual | virtual | 4GB |  | RHEL5 | [6 empty] | already virtual, could be moved to dev stack easily |  |  | dev stack | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | RHEL6
MEDIA SERVERS | [15 empty] | MEDIA SERVERS
Production Streaming Server (used by Lecturecast, Lunch Hour Lectures live streaming etc) | j.norton@ucl.ac.uk is-windows@ucl.ac.uk isd-ats@ucl.ac.uk mm-productions@ucl.ac.uk | fms-a.uclw | physical (Wolfson House) | 2009-04-29 | 2 x quad core Xeon @ 3.33GHz | 8GB | C: 23 GB Free (40 GB Total) D: 773 Gb Free (1637 Gb Total) | Windows 2008 | Adobe FMIS 3.5 (and in-house live streaming secure app) |  | 863 Gb (53%) in use of existing physical storage on local D: already used (by Lecturecast and Multimedia + UCL Advances VOD uploads) | Lecturecast: 1.1 Tb Multimedia VOD + iTunes uploads: 196 Gb Multimedia HD + Dynamic Streaming: 598 Gb iTunes existing content (migrated from XSAN): 1772 GB UCL Advances Video Portal: 800 Gb Great Ormond Street: ?? Mediacast (user generated content): ?? TOTAL: 4,492 Gb | Lecturecast: 5.6 Tb Multimedia VOD + iTunes uploads: 416 Gb Multimedia HD + Dynamic Streaming: 1270 Gb iTunes existing content (migrated from XSAN): 1772 GB UCL Advances Video Portal: 1731 Gb Great Ormond Street: ?? Mediacast (user generated content): ?? TOTAL: 10,923 Gb | Lecturecast: 9.2 Tb Multimedia VOD + iTunes uploads: 663 Gb Multimedia HD + Dynamic Streaming: 2027 Gb iTunes existing content (migrated from XSAN): 1772 GB UCL Advances Video Portal: 2795 Gb Great Ormond Street: ?? Mediacast (user generated content): ?? TOTAL: 16,679 Gb | likely to run out of disk space by xxxx | Production Streaming Server (used by Lecturecast, Lunch Hour Lectures live streaming etc) | vmstreaming-a.uclw | ? | small | 2 | 4 Gb | 40 | 16678 |  |  | 0 | 122783.6 | Windows 2008 R2 |  | depends on outcome of streaming evaluation |  | high importance | streaming.ucl.ac.uk points at fms-a and fms-b, sending users to the server with least load.· streaming-upload.ucl.ac.uk points at fms-a unless fms-a fails, in which case it automatically fails over to fms-b· streaming-live.ucl.ac.uk points at fms-a unless fms-a fails, in which case it automatically fails over to fms-b · Note that the FMIS licence key from fms-a needs to be manually transferred to fms-b in the event of fms-a failing to keep the live streaming service running. DFS replication of media files (in applications/vod/media folder) to keep fms-a and fms-b in sync |  |  | do we still need to servers in the virtual world??
|  | fms-b.uclw | physical (KLB) | 2009-04-29 | 2 x quad core Xeon @ 3.33GHz | 8GB | C: 21 GB Free (40 GB Total) D: 645 Gb Free (1637 Gb Total) | Windows 2008 | Adobe FMS 3.5 |  | 991 Gb (61%) in use of existing physical storage on local D: already used (by Lecturecast and Multimedia + UCL Advances VOD uploads) | [5 empty] | vmstreaming-b.uclw |  | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2
Development streaming server |  | fms-dev.uclw | physical (Wolfson House) | 2009-04-29 | 2 x quad core Xeon @ 3.33GHz | 8GB | C: 22 GB Free (40 GB Total) D: 1 TB Free (1.6TB Total) | Windows 2008 | Adobe FMIS 3.5 (free development licence, max 10 concurrent users) | [6 empty] | Development streaming server | vmstreaming-dev.uclw | dev stack | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 |  | depends on outcome of streaming evaluation
Multimedia Wowza server |  | wowza.mediares.ucl.ac.uk | virtual (on Multimedia standalone box) | late 2009 (VMware host) | host has 2 x Xeons @ 3ghz | 4GB configured | 7GB Free (10GB Total) |  | Wowza
Sawmill (streaming stats) |  | uclusers-la1.uclusers | virtual, but not on central stack | - | 2 CPU's | 4GB | 24 Free / 60Gb Total | Windows 2008 R2 | Sawmill SQLite or similar? |  | - | - | - | - | - | Sawmill (streaming stats) does this need its own server?? | uclusers-la1.uclusers | ? | medium | 4 | 8 Gb | 60 | 0 |  |  | 0 | 5115 | Windows 2008 R2 |  | depends on outcome of streaming evaluation
Production Lecturecast | j.norton@ucl.ac.uk ltss-team@ucl.ac.uk is-windows@ucl.ac.uk isd-ats@ucl.ac.uk | lcess1.uclw | physical (Wolfson House) | 2010-03-31 | 2 x quad core Xeon X5570 | 4GB | 203 GB Free (278Gb Total) | Windows 2008 R2 | EchoSystem Server (ESS) SFTP Jetty | [6 empty] | Production Lecturecast | lcess1.uclw | HA ? | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 | EchoSystem Server (ESS) SFTP Jetty |  |  | high importance
|  | - | - | - | - | - | - | - | - | [7 empty] | lcess2.uclw |  | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2
|  | lcencode1.uclw | physical (Wolfson House) | 2010-03-31 | 2 x quad core Xeon X5570 | 4GB | 258 GB Free (278 Gb Total) | Windows 2008 R2 | EchoSystem Media Processor | [7 empty] | lcencode1.uclw |  | medium | 4 | 8 Gb | 60 | 0 |  |  | 0 | 5115 | Windows 2008 R2 | EchoSystem Media Processor
|  | lcencode2.uclw | physical (Wolfson House) | 2010-03-31 | 2 x quad core Xeon X5570 | 4GB | 243 GB Free (278 Gb Total) | Windows 2008 R2 | [8 empty] | lcencode2.uclw |  | medium | 4 | 8 Gb | 60 | 0 |  |  | 0 | 5115 | Windows 2008 R2
|  | lcww1.uclw | physical (Wolfson House) | 2010-03-31 | 2 x quad core Xeon X5570 | 4GB | 262 GB Free (278 Gb Total) | Windows 2008 R2 | IIS | [7 empty] | lcww1.uclw |  | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 | IIS
|  | - | - | - | - | - | - | - | - | [7 empty] | lcww2.uclw |  | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2
UAT (pre-production) Lecturecast |  | - | - | - | - | - | - | - | - | - | [5 empty] | UAT (pre-production) Lecturecast | lcess1-uat.uclw | dev stack | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 | EchoSystem Server (ESS), SFTP, Jetty
|  | - | - | - | - | - | - | - | - | - | [6 empty] | lcencode1-uat.uclw |  | medium | 4 | 8 Gb | 60 | 0 |  |  | 0 | 5115 | Windows 2008 R2 | EchoSystem Media Processor
|  | - | - | - | - | - | - | - | - | - | [6 empty] | lcww1-uat.uclw |  | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 | IIS
Development Lecturecast |  | lcess1-dev.uclw | virtual dev stack |  | 2 CPU's | 4GB | 44 GB Free (60 GB Total) | Windows 2008 R2 | EchoSystem Server (ESS), SFTP, Jetty | [6 empty] | Development Lecturecast | lcess1-dev.uclw | dev stack | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 | EchoSystem Server (ESS), SFTP, Jetty
|  | lcencode1-dev.uclw | virtual dev stack |  | 2 CPU's | 4GB | 46 GB Free (60GB Total) | Windows 2008 R2 | EchoSystem Media Processor | [7 empty] | lcencode1-dev.uclw | dev stack | medium | 4 | 8 Gb | 60 | 0 |  |  | 0 | 5115 | Windows 2008 R2 | EchoSystem Media Processor
|  | lcww1-dev.uclw | virtual dev stack |  | 2 CPU's | 2GB | 30 GB Free (40 GB Total) | Windows 2008 R2 | IIS | [7 empty] | lcww1-dev.uclw | dev stack | small | 2 | 4 Gb | 40 | 0 |  |  | 0 | 2702 | Windows 2008 R2 | IIS
iTunes U (would need to relocate to virtual linux webserver if/when we decomission Apple stack) | j.norton@ucl.ac.uk r.bartholomew@ucl.ac.uk is-macosteam@ucl.ac.uk isd-ats@ucl.ac.uk mm-productions@ucl.ac.uk | - | - | - | - | - | - | - | - | - |  |  |  |  | iTunes currently run on Apple Podcast Producer servers, PcP has known problems and needs frequent restarting | Production iTunes U | vmitunes-a | HA ? | small | 2 | 4 Gb | 40 | 0 | 0 | 0 | 0 | 2702 | RHEL6 |  |  |  | high importance
[16 empty] | Dev iTunes U | vmitunes-dev | dev stack | small | 2 | 4 Gb | 40 | 0 | 0 | 0 | 0 | 2702 | RHEL6
UCL Advances video portal http://www.londonentrepreneurshiponline.com/ | ucladvances-videoportal-support@ucl.ac.uk k.macmillan@ucl.ac.uk | videoportal-a.uclw | physical (Wolfson House) | purchased 19/12/2007, warrenty expiry 18/12/2012 | 2 x quad core Xeon x5450 @ 3 GHz (8 cores) | 8 GB | 2 x 146 GB mirrored, so 146 GB usable: 99 GB free application |  | apache | Joomla based website | [5 empty] | UCL Advances video portal http://www.londonentrepreneurshiponline.com/ | videoportal-a.uclw | BH | medium | 4 | 8 Gb | 60 | 0 |  |  |  | 5115 | RHEL5 x86_64 (Redhat Enterprise Linux v5, 64 bit) | apache | Joomla based website |  |  | using network slb configured to failover on to videoportal-b upon videoportal-a failure | it depends upon user requirements, but from the past experience with UCL Advances only asking for one server, I would say only one server needed and snapshots done before changes to are made to software. being virtual on a stack means there are no concerns about hardware or site failure which is one of the main reasons for having two servers in the past
|  | videoportal-b.uclw | virtual | - | 1 core x Xeon x5450 @ 3 GHz | 1GB | 36 GB (30 GB free) | RHEL5 x86_64 (Redhat Enterprise Linux v5, 64 bit) | apache | Joomla based website
server size | processor (core cycles) | memory (GBs) | storage (GBs) | cost for a Dred VM server |  |  | Additional Tier 1 storage (per Gb) |  | 7.2 | Tier 1 Storage |  |  |  | Tier 2 Storage
small | 2 | 4 Gb | 40 | 2702 |  |  | Additional Tier 2 storage (per Gb) |  | 1.2 | RAID5, SVC Mirrored, Nightly backup to tape |  |  |  | RAID5, Nightly backup to tape
medium | 4 | 8 Gb | 60 | 5115 | [5 empty] | Operating SLA - 99.9% to 99.99% availability, Very high data integrity |  |  |  | Operating SLA - 99.8% availability, Good data integrity
large | 8 | 16 Gb | 100 | 9947 | [5 empty] | DR SLA - Recovery point objective (RPO) = 0 Seconds, Recovery Time Objective (RTO) = Sub seconds |  |  |  | DR SLA - RPO = 24 Hours, RTO = 1 Month

## Sheet2
1126 | 5734 | 9421
196 | 416 | 663
598 | 1270 | 2027
1772 | 1772 | 1772
800 | 1731 | 2795
4492 | 10923 | 16678