## Sheet1
| WEEK | 2014-01-27 | 2014-02-03 | 2014-02-10 | 2014-02-17 | 2014-02-24 | 2014-03-03 | 2014-03-10 | 2014-03-17 | 2014-03-24 | 2014-03-31 | 2014-04-07 | 2014-04-14 | 2014-04-21 | 2014-04-28 | 2014-05-05 | 2014-05-12 | 2014-05-19 | 2014-05-26 | 2014-06-02 | 2014-06-09 | 2014-06-16 | 2014-06-23 | 2014-06-30 | 2014-07-07 | 2014-07-14 | 2014-07-21 | 2014-07-28 | 2014-08-04
Who
TRACK
Theme
Specify theme requirements | ELE | 2014-03-31: 2014-04-01
Check against wish list | bar: 2014-02-24
Version ready for initial response - create decision point list |  | 2014-03-10: 2014-03-10
Gather feedback - decide colours | bar: 2014-03-17
Detailed spec for developer | bar: 2014-03-24
Design Theme | LTA/ELE | 2014-03-31: 2014-04-02; 2014-05-05: 2014-05-02
Mobile testing? |  | 2014-06-09: finish testing
Accessibility testing | bar: 2014-03-31 to 2014-06-09
Test browser compatibility with browsers supported at UCL | bar: 2014-03-31 to 2014-06-09
Test core functionality | bar: 2014-03-31 to 2014-06-09
ELE
Testing functionality - new features plus custom plugins |  | 2014-03-17: 2014-03-17; 2014-05-12: 2014-05-16
Review the admin settings and document changes - date? |  | 2014-03-24: 2014-03-28
Document new 2.6 features and changes for end users |  | 2014-05-12: Re-work Moodle Resource Centre; 2014-06-23: 2014-06-23
Comms
Advertise outage - date? | bar: 2014-02-24
Create info page | bar: 2014-03-03
Speak Med School
Anounce new support docs |  | 2014-07-07: 8,9,10/6/2014
LTA
Appoint theme contractor? | LTA | 2014-03-03: 2014-03-03
Upgrade UCL moodle to 2.6 without ucl themes on moodle-dev |  | 2014-03-17: 2014-03-21
Make UAT version available |  | 2014-04-21: 2014-04-25
Review the currently used plugins and document compatibility with 2.6 |  | 2014-03-24: 2014-03-28
Implement SITS filter |  | 2014-07-28: Test and Implement SITS Filter
Performance testing |  | 2014-06-02: 2014-06-02; 2014-06-16: 2014-06-13
Fix issues post UAT Testing |  | 2014-06-16: 16/06/2014 - 20/06/2014
Code Freeze |  | 2014-06-16: 20/06/14 Code Freeze
Dry run upgrade |  | 2014-06-23: 23/06/2014 -> Upgrade moodle-dev, Upgrade moodle-test, 24/06/2014 -> upgrade moodle-uat, 26/06/2014 -> Upgrade moodle-loadtest
Other LTA pre-upgrades tasks?
Other LTA pre-upgrades tasks?
Archive |  | 2014-07-07: 04/07/2014 - 05/07/2014
Upgrade |  | 2014-07-07: 04/07/2014- 09/07/2014
Note on G6: Martin Burrow: I put some comments on jess and mira page in wiki. Not much leeway to address everything now.