## Phase 1
Project name : ELE-Integration
Phase 1
Iteration 1
No | Tasks | Status | Notes | Days
1 | Read data from views and dump into moodle_sits_management_dev2 database |  | Views : MOODLE_V_CMIS_MODGRP, MOODLE_V_CMIS_STUGRP moodle_sits_management_dev2 database Tables : cmis_groups_dump, cmis_group_members_dump | 2
Import data from CMIS and create groups in Moodle
2 | Read data from dump table and insert into cmis_groups table Map the groups to their associated courses. Use mapped_modules to get courseids for modules |  | Tables : moodle_sits_management_dev2.cmis_groups, moodle_sits_management_dev2.cmis_course_groups | 3
3 | Establish successful handshaking between client(cmis on moodle-admin-dev) and server (moodle dev instance on moodle-dev) |  | Make sure you have following Server : moodle-dev (https://el-int.moodle-dev.ucl.ac.uk) token : get token ele-int instance Run moodle test client to check if we have REST service working as expected | 0.5
4 | Create groups within Moodle |  |  | 1.5
5 | Record response received from Moodle after REST call into table within moodle_sits_managment_dev2 |  | Table : moodle_sits_management_dev2.cmis_moodle_groups | 2
6 | Rest Response and Exception Handler |  |  | 1.5
Iteration 2
No | Tasks | Status | Notes | Days
Delete groups
1 | Read data from cmis_groups and cmis_groups_course. Get groups with 'todelete' flag set to 1 |  | Tables : moodle_sits_management_dev2.cmis_groups, moodle_sits_management_dev2.cmis_course_groups | 4
2 | Establish successful handshaking between client(cmis on moodle-admin-dev) and server (moodle dev instance on moodle-dev) |  | Make sure you have following Server : moodle-dev (https://el-int.moodle-dev.ucl.ac.uk) token : get token ele-int instance Run moodle test client to check if we have REST service working as expected
3 | Delete groups within Moodle |  |  | 0.5
4 | Record response received from Moodle after REST call into table within moodle_sits_managment_dev2 |  | Insert into - Table : moodle_sits_management_dev2.cmis_groups_deleted Delete records from - Tables : moodle_sits_management_dev2.cmis_groups, moodle_sits_management_dev2.cmis_course_groups Update records in - Table : moodle_sits_management_dev2.cmis_groups_moodle | 1
5 | Reset all add, update, delete and found flags to 0 |  | Table : moodle_sits_management_dev2.cmis_course_groups | 1
6 | Rest Response and Exception Handler |  |  | 1

## Phase 2
Project name : CMIS Moodle Interface
Phase 1
Iteration 1
No | Tasks | Status | Notes | Days
Import data from CMIS and insert members into groups in Moodle
1 | Read data from dump table and insert into cmis_groups table Map the groups to their associated courses. Use mapped_modules to get courseids for modules |  | Tables : TBC | 4
2 | Establish successful handshaking between client(cmis on moodle-admin-dev) and server (moodle dev instance on moodle-dev) |  | Make sure you have following Server : moodle-dev (https://el-int.moodle-dev.ucl.ac.uk) token : get token ele-int instance Run moodle test client to check if we have REST service working as expected | 0.5
3 | Adding users to the groups |  |  | 1.5
4 | Record response received from Moodle after REST call into table within moodle_sits_managment_dev2 |  | Tables : TBC | 2